## SF Budget Template
Safaricom Foundation
Organisation | Kivuli Innovation and Incubation Center
Project title | Kivuli Youth Network (Mwai Abiero Ogen Secondary School Hub)
Date | 27/8/2020
Total amount for the project | #REF!
Total for the project
Outcome description | Activity description | Details/ budget justification | Units/ Number | Unit cost/Rate (KShs) | Amount (KShs)
Outcome 1 | Activity 1.1
School drop out rate reduced by 10% by end of 2021 | Recruit and train volunteer mentors | Conference package for 10 volunteer mentors and 5 Project Team for 4 days | 60 | 500 | 30000
|  | Transport Reimbursement for 10 volunteer mentors and 5 Project Team for 4 days | 60 | 500 | 30000
| Total for activity 1.1 |  |  |  | 60000
Activity 1.2
| Mentor Students | 10 mentors to meet the 70 mentees also members of the entrepreneurship club for not less than 1 hour per month. Mentors will follow the Kivuli Mentorship Guide. | 240 | 1000 | 240000
| Total for activity 1.2 |  |  |  | 240000
Activity 1.3
| Strengthen sports recreation for students by providing uniforms to 1 boys' football team and 1 girls' netball team | Full uniform for boys' footbal team consisting of 11 players, 3 reserve players and a coach | 15 | 5000 | 75000
|  | Full uniform for girls' netball team consisting of 7 players, 4 reserve players and a coach | 12 | 3000 | 36000
| Total for activity 1.3 |  |  |  | 111000
Activity 1.4
| Strengthen sports recreation for students by sponsoring yearly sports days | Certificates and medals for participants in 1st - 3rd positions for 7 games each conducted 5 times | 210 | 350 | 73500
|  | Trophies for the top 3 teams for each sports day | 6 | 5000 | 30000
|  | Logistics and firstaid - preparing fields for each sports day and first aid attendants | 2 | 5000 | 10000
| Total for activity 1.4 |  |  |  | 113500
Activity 1.5
| Customize an entrepreneurship training manual for youth | Consultancy services of an expert in entrepreneurship for 15 days - guide in selection of various manuals to customize from, develop the customized manual, sensitize participants on the customized manual | 15 | 5000 | 75000 | Here we can get a lecturer from one of these institutions, I think they'd be cheaper. Coz a fulltime experienced consultant might be very expensive. We just advertise at akina Kisumu Poly, KIM, KCA, UON…at institutions where entrepreneurship is taught
|  | 4 - day conference package, full board in Kisumu for 7 to initiate development of the manual with the consultant and sensitization meeting for final copy - Consultant, Business studies teacher from Mwayi Abiero, Project Coordinator, Accountant, 3 Kivuli Board members | 28 | 3000 | 84000
|  | Transport reimbursement for 6 participants | 6 | 2000 | 12000
| Total for activity 1.5 |  |  |  | 171000
Activity 1.6
| Strengthen extra curricular activities for students by establishing an Entrepreneurship and Leadership club | Seed capital for the club | 1 | 15000 | 15000 | Some start up money to help them buy a few materials for the club
| Total for activity 1.6 |  |  |  | 15000
Activity 1.7
| Organize 1-day bi-annual seminars on Entrepreneurship and Leadership | 2 speakers | 4 | 5000 | 20000
|  | Conference package for 70 students, 2 speakers and 5 project team | 154 | 500 | 77000
| Total for activity 1.7 |  |  |  | 97000
Activity 1.8
| Organize quarterly learning programs to different establishments | Bus transport for 70 students, patron and project coordinator - 8 learning trips in total | 8 | 5000 | 40000
|  | Lunch for 70 students, patron and project coordinator - 8 learning trips in total | 576 | 200 | 115200
| Total for activity 1.8 |  |  |  | 155200
Activity 1.9
| Organize annual exhibitions for the club - invite community members, teachers, parents, students and board | Exhibition booths and marketing material | 1 | 20000 | 20000
| Total for activity 1.9 |  |  |  | 20000
Activity 1.10
| Project Management, Monitoring and Evaluation | Salary for Project Coordinator - monthly | 8 | 70000 | 560000
|  | Salary for part-time Project Acountant - monthly | 8 | 10000 | 80000
|  | Conduct a one-time project launch with teachers, school board and other relevant stakeholders - total of 30 invitees | 1 | 6000 | 6000 | PME=174,050 (6.5%)
|  | Quarterly project monitoring meetings conducted by the project team, and Kivuli board - 7 people in attendance | 4 | 2000 | 8000 | HR=1,920,000 (72.46%)
|  | Monitoring and Evaluation - manage monthly data collection and anlysis. Prepare monthly, quarterly and yearly reports. | 1 | 33350 | 33350 | Beneficiaries = 550,500 (20.9%)
|  | Communication - manage quarterly social media visibility and publications. | 4 | 5000 | 20000 | Total =2,649,550
| Total for activity 1.10 |  |  |  | 707350
Total for outcome 1 |  |  |  |  | 1690050
Outcome 2 | Activity 2.1
Youth have the capacity to successfully innovate and implement ideas during the project period. | Impart entrepreneurship skills, life skills and soft skills to 70 students during bi-monthly club days | Patron/business studies teacher/guidance and counselling teacher to build the students' capacity in entrepreneurship, life and soft skills | 24 | 1000 | 24000
| Total for activity 2.1 |  |  |  | 24000
Activity 2.2
| Project Management, Monitoring and Evaluation | Salary for Project Coordinator - monthly | 8 | 70000 | 560000
|  | Salary for part-time Project Acountant - monthly | 8 | 10000 | 80000
|  | Conduct a one-time project launch with teachers, school board and other relevant stakeholders - total of 30 invitees | 1 | 6000 | 6000
|  | Quarterly project monitoring meetings conducted by the project team, and Kivuli board - 7 people in attendance | 2 | 2000 | 4000
|  | Monitoring and Evaluation - manage monthly data collection and anlysis. Prepare monthly, quarterly and yearly reports. | 1 | 33350 | 33350
|  | Communication - manage quarterly social media visibility and publications. | 2 | 5000 | 10000
| Total for activity 2.2 |  |  |  | 693350
Total for outcome 2 |  |  |  |  | 717350
Outcome 3 | Activity 3.1
Transition rate to institutions of higher learning improved by at least 10% by end of 2021 | Facilitate establishment of a career guidance and counselling department by sponsoring one teacher to attend guidance and counselling training at certificate level | Training fees for one teacher | 1 | 12000 | 12000
| Total for activity 3.1 |  |  |  | 12000
Activity 3.2
| Equip guidance and counselling department with a computer and internet connection for online resources and references | Computer | 1 | 20000 | 20000
|  | Monthly Internet connection for online resources and references | 24 | 1500 | 36000
| Total for activity 3.2 |  |  |  | 56000
Activity 3.3
| Organize Career Days | Sponsor an annual career day at the school open to all students - invite 5 speakers | 1 | 40000 | 40000 | each speaker to receive about 5k and then refreshments for board members, speakers and teaching fraternity and students 15k
| Total for activity 3.3 |  |  |  | 40000
Activity 3.4
| Project Management, Monitoring and Evaluation | Salary for Project Coordinator - monthly | 8 | 70000 | 560000
|  | Salary for part-time Project Acountant - monthly | 8 | 10000 | 80000
|  | Conduct a one-time project launch with teachers, school board and other relevant stakeholders - total of 30 invitees | 1 | 6000 | 6000
|  | Quarterly project monitoring meetings conducted by the project team, and Kivuli board - 7 people in attendance | 2 | 2000 | 4000
|  | Monitoring and Evaluation - manage monthly data collection and anlysis. Prepare monthly, quarterly and yearly reports. | 1 | 33350 | 33350
|  | Communication - manage quarterly social media visibility and publications. | 2 | 5000 | 10000
| Total for activity 3.4 |  |  |  | 693350
Total for outcome 3 |  |  |  |  | 801350
TOTAL |  |  |  |  | #REF!
Guidance notes
1. Please fill in the name of the organisation, project title and date in the sections above.
2. Please indicate the outcome headings and list the corresponding activities and details of the activities.
3. Please state the number of units, unit rates and total amounts for the whole project period
4. If a budget line does not apply to your project, do NOT leave the space blank; write " N/A" instead
5. Project expenses should be clearly identified in the appropriate budget line
6. The total amount for the project indicated in row 6 should be the same as the total indicated in row 37
7. Please note that your budget needs to be reviewed by the Safaricom Foundation for approval
8. Definitions:
Outcome: the changes, benefits, learning or other effects that happen as a result of services and activities provided by an organisation
Activity: The actions, tasks and work a project or organisation carries out to create its outputs and outcomes, and achieve its aims
9. Please insert additional rows, as necessary.

## Example Budget
Safaricom Foundation
Organisation | Example
Project title | Example
Date | 2020-10-19
Total amount for the project | #REF!
|  |  | Total for the project |  |  |  |  | PERIOD 1 |  | PERIOD 2 |  | PERIOD 3 |  | PERIOD 4 |  | Total Year 1 |  | Year 2 |  | Year 3
Outcome description | Activity description | Details/ budget justification | Cost/Unit | No of participants | Quantity | Unit | Amount (GBP) | Units/ Number | Amount (GBP) | Units/ Number | Amount (GBP) | Units/ Number | Amount (GBP) | Units/ Number | Amount (GBP) | Units/ Number | Amount (GBP) | Units/ Number | Amount (GBP) | Units/ Number | Amount (GBP)
Outcome 1 | Activity 1.1
Increasing access to educational opportunities for children with disabilities | Teaching the disabled children to learn | Teachers transport | 100 | 2 | 5 | lumpsum | 1000 | 5 | 1000 | [6 empty] | 5 | 1000
|  | Hall rent | 1000 | 1 | 5 | days | 5000 | 5 | 5000 | [6 empty] | 5 | 5000
| Total for activity 1.1 | [5 empty] | 6000 |  | 6000 |  | 0 |  | 0 |  | 0 |  | 6000
Activity 1.2
| Learning materials developed. | Stationery | 50 | 20 | 5 | lumpsum | 5000 |  |  | 5 | 250 |  |  |  |  | 5 | 250
|  | Furniture and fittings | 250 | 1 | 3 | lumpsum | 750 |  |  | 3 | 750 |  |  |  |  | 3 | 750
| Total for activity 1.2 | [5 empty] | 5750 |  |  |  | 1000 |  | 0 |  | 0 |  | 1000
TOTAL | [6 empty] | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!

## SF Project Workplan Template
Safaricom Foundation
Organisation |  | Kivuli Innovation and Incubation Center
Project title |  | Kivuli Youth Network (Mwai Abiero Ogen Secondary School Hub)
Date |  | 27/8/2020
Annex B: Project Workplan
Outcomes and Activities |  |  | Year | [11 empty] | Year
|  | Responsibility | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Programme management and set up
For example initial project meetings or management/committee meetings
Outcome 1 | School drop out rate reduced by 10% by 2021
Activity 1.1 | Recruit and train mentors | bar: Year J to Year F
Activity 1.2 | Mentor Students
Activity 1.3 | Provide uniforms to 1 boys' football team and 1 girls' netball team | bar: Year F
Activity 1.4 | Sponsor yearly sports days | bar: Year J; Year J
Activity 1.5 | Customize an entrepreneurship training manual for youth | bar: Year J
Activity 1.6 | Establish and support Leadership and Entrepreneurship Club
Activity 1.7 | Sponsor 1-day bi-annual seminars on leadership and entrepreneurship | bar: Year A; Year A; Year A; Year A
Activity 1.8 | Sponsor annual exhibitions for the club | bar: Year D; Year D
Activity 1.9 | Organize quarterly learning programs to different establishments | bar: Year M; Year J; Year S; Year D; Year M; Year J; Year S; Year D
Activity 1.10 | Project Management, Monitoring and Evaluation
Outcome 2 | Youth have the capacity to successfully innovate and implement ideas during the project period
Activity 2.1 | Impart entrepreneurship skills, life skills and soft skills
Activity 2.2 | Project Management, Monitoring and Evaluation
Outcome 3 | Transition rate to institutions of higher learning improved by at least 10% by end of 2021
Activity 3.1 | Sponsor a teacher to train in guidance and counselling | bar: Year F
Activity 3.2 | Equip guidance and counselling department and support guidance and counselling to students
Activity 3.3 | Organize Career Days | bar: Year M; Year M
Activity 3.4 | Project Management, Monitoring and Evaluation
Guidance notes
1. Please shade in the period in which the activity described will occur.
2. Whether you use various colours (some find it helpful) or simply black or grey.
3. Please note that this workplan is intended to provide an overview of the expected work to be completed in the proposed period.
4. Please provide a reasonable timeline for the expected dates for the completion of the proposed project
5. Please insert additional rows, and columns as necessary.
6. Please note that your workplan needs to be reviewed by the Safaricom Foundation for approval
7. Definitions:
Outcome: the changes, benefits, learning or other effects that happen as a result of services and activities provided by an organisation
Activity: The processes that an organisation will carry out
Responsibility: The person in charge of carrying out the task should be indicated

## Example Project Workplan
Safaricom Foundation
Organisation |  | 0
Project title |  | 0
Date |  | 0
Annex B: Project Workplan
outcomes and Activities |  |  | 2014
|  |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
Programme management and set up
For example initial project meetings or management/committee meetings | bar: 2014 J
outcome 1 | Increasing access to educational opportunities for children with disabilities
Activity 1.1 | Teaching the disabled children
Activity 1.2 | Learning materials developed. | bar: 2014 F to 2014 M
Activity 1.3 | Building schools | bar: 2014 A to 2014 D
outcome 2 | Increasing access to educational opportunities for children from nomadic pastoralist communities
Activity 2.1 | Creating awareness | bar: 2014 F to 2014 J
Activity 2.2 | Learning materials developed. | bar: 2014 F to 2014 M
Activity 2.3 | Building schools
outcome 3 | Increasing access to ICT education for both teachers and students
Activity 3.1 | Training teachers | bar: 2014 F to 2014 A
Activity 3.2 | Buying computers | bar: 2014 J
Activity 3.3 | Building schools
outcome 4 | Improving both teacher and student competencies in literacy and numeracy (particularly mathematics)
Activity 4.1 | Training teachers | bar: 2014 F to 2014 M
Activity 4.2 | Building schools
Activity 4.3 | Learning materials developed. | bar: 2014 F to 2014 A
Guidance notes
1. Please shade in the period in which the activity described will occur.
2. Whether you use various colours (some find it helpful) or simply black or grey.
3. Please note that this workplan is intended to provide an overview of the expected work to be completed in the proposed period.
4. Please provide a reasonable timeline for the expected dates for the completion of the proposed project
5. Please insert additional rows, and columns as necessary.
6. Please note that your workplan needs to be reviewed by the Safaricom Foundation for approval
7. Definitions:
Outcome: the changes, benefits, learning or other effects that happen as a result of services and activities provided by an organisation
Activity: The processes that an organisation will carry out
Responsibility: The person in charge of carrying out the task should be indicated